## Role Breakdown
Team N²M — Predictive Flood Alert System — Role Breakdown
1BCP308 – Community Project ¦ Domain: Space & Earth Observation ¦ Faculty Guide: Prof. Punith Kumar
Member | Role / Deliverable | Core Tasks | Skills to Learn | Timeline | Notes / Key Resources
Nishanth (You) | Member 1 — Data Collection & Pre-processing | Source historical rainfall (IMD/KSNDMC); pull Sentinel-1 SAR imagery via Google Earth Engine; get SRTM DEM terrain data; classify SAR into water/no-water; align rainfall + flood-extent + terrain into one clean dataset by date and zone. | Google Earth Engine (Python API); SAR water classification; geospatial data alignment. Side-track: Kaggle Intro/Intermediate ML (XGBoost lesson), ~1–2 hrs/week, no pressure. | Weeks 1–4: source + clean data (blocks Member 2). Ongoing: support teammates as data questions arise. | Directly reuses Integral Geo skills: geocoding, structuring messy govt data, SQLite schema design.
Teammate A | Member 3 — Systems Integration | Build live rainfall-forecast API pipeline feeding the model; build Telegram bot that alerts when risk crosses threshold; build Leaflet map showing live + historical (replay) risk levels. | REST API calls; Telegram Bot API; Leaflet.js (reuse Nishanth's Integral Geo map template). | Weeks 1–2: learn Telegram Bot API + adapt Leaflet template (can start with dummy data). Weeks 3–6: wire up live pipeline once Member 2 has a callable model. | Key resource: official Telegram Bot API docs — a working bot is a few hours' work.
Teammate B | Member 2 — ML Model | Feature engineering (with Nishanth's help) from the cleaned dataset; train an XGBoost baseline model (rainfall + terrain → flood risk score); evaluate; optionally attempt an LSTM as a stretch goal. | pandas/numpy; train/test split + evaluation metrics (F1 or RMSE); XGBoost; (stretch) Keras LSTM. | Weeks 1–3: Kaggle Intro + Intermediate ML courses. Weeks 4–5: first XGBoost model on real data (needs dataset from Week 4). Week 6+: tuning, stretch LSTM if time allows. | Key resource: Kaggle “Intro to Machine Learning” → “Intermediate Machine Learning” (free, hands-on, ends in XGBoost).
Cross-Team Notes
• Member 2 is blocked until Member 1 has a usable dataset — front-load data work in Weeks 1–4.
• Member 3 needs a working model to call before building the live pipeline — Leaflet/bot skeleton can be built early with dummy data, then wired to the real model later.
• Aim for a rough end-to-end version (even if inaccurate) by Review 2, then spend Reviews 3–4 improving accuracy and polishing the demo/replay.